## Cover
Defect Tracking Sheet
Project Name
Version No. (Latest Version) | Release Date | Modified by Date | Reviewed by Date | Authorized by Date | Remarks
Revision History sheet
Version No. <all previous version> | Release Date | Modified by Date | Reviewed by Date | Authorized by Date | Remarks

## Defect Report-Review Log
Project Id. |  | Project Name
Test/ Review Type |  | Module Name
Work Product / Code ID |  | Work Product / Code Name
Work Product / Code developed by |  | Test/ Review Date
Tested / Reviewed By
Test Case Id | Test Condition | Expected Result | Actual Result / Description | Affected Work Products | Defect Severity | Defect Sub Sub severity | Defect Initiation Phase | Defect Cause | Assigned To | Estimated Effort (hrs.) | Planned Start Date | Planned End Date | Actual start date | Actual End Date | Actual effort spent (hrs) | Status | Remarks
t001 | click on book appoitment | it should accept data and book the app | throwing an erroer. | p001 | show stopper |  | function testing
t002 | enter invalid date | should give a message saying it’s a invalid date | allowing to proceed further | p002 | medium |  | unit testing

## Guidelines
Field | Explanation
Test Cases Sheet
Project Id | Specify the project id
Project Name | Specify the project Name
Test | User Acceptance Testing
Module Name | Specify the module name, if applicable
Test Cases Code developed by | Specify the name of the person (s) who has developed the test cases
Test Case Preparation Date | Specify the date of preparation of test cases
Test case Id | Specify unique running id for all the test cases
Test Condition | Specify the test condition
Test Data | Specify the test data tobe used with the test condition
Expected Result | Specify the expected result for every test condition
Actual Result / Description | Specify the actual result of testing or give description of the review finding
Defect Report - Review Log Sheet
Note: | For review defects, test id, test condition and expected result column should be left blank
Project Id | Specify the project id
Project Name | Specify the project Name
Test / Review Type | User Acceptance Testing
Module Name | Specify the module name, if applicable
Work Product / Code ID | Specify the Work Product / Code ID
Work Product / Code Name | Specify the Work Product / Code Name
Work Product / Code developed by | Specify the name of the person (s) who has developed the code / prepared the work product
Tested / Reviewed By | Name of the person who tested / reviewed
Test / Review Date | Specify the date of conducting test/ review
Test case Id | Specify unique running id for all the test cases
Test Condition | Specify the test condition
Expected Result | Specify the expected result for every test condition
Actual Result / Description | Specify the actual result of testing or give description of the review finding
Affected Work Products | List of the module/ function/ programs impacted by this bug.
Defect Severity | indicates the type of the bug reported. It can have following values -
A - fatal errors (testing unit can not be executed further)
B - Critical errors ( functionality errors but execution is not halted)
C - Minor functionality errors.
D - Cosmetics errors. ( e.g. GUI, color etc )
Defect Sub Severity | For Severity A: FN - Functional LG - Logical IN - Interface UI - User Interface CO - Communication PE- Performance BR - Boundary Related CL- Calculation
For Severity B: FN - Functional LG - Logical IN - Interface UI - User Interface CO - Communication PE- Performance BR - Boundary Related CL- Calculation
For Severity C: LG - Logical IN - Interface UI - User Interface CO - Communication CL- Calculation
For Severity D: UI - User Interface
Defect Initiation Phase | PDLC Phase in which the defect was injected. It can have the following values:
S - System Feasibility
R - Requirements Phase
D - Design
C - Construction
T- Testing
Defect Cause | Specify from the following list: Coding Error Cosmetic Error Configuration Error Design Error Setup Error Functionality Error Inadequate Design Skills Inadequate Documentation Inadequate Functional Requirements Inadequate Functional Skills Inadequate Functional Training Inadequate General Communication Inadequate Intra-Team Communication Inadequate Standards Inadequate Technical Skills Inadequate Technical Training Inadequate Testing Skills Inadequate Tools Inadequate Tools Skills Inadequate Tools Training Inadequate User Training Installation Error Misinterpretation Not An Error Requirements Error
Root cause | Cosmetic Error Inadequate Design Skills Inadequate Documentation Inadequate Functional Requirements Inadequate Functional Skills Inadequate Functional Training Inadequate General Communication Inadequate Intra-team Communication Inadequate Standards Inadequate Technical Skills Inadequate Technical Training Inadequate Testing Skills Inadequate Tools Inadequate Tools Skills Inadequate Tools Training Inadequate User Training Installation Error Misinterpretation
Assigned to | correction assigned to the code developer
Estimated Effort | Effort estimated to rectify the defect
Planned Start Date | Planned start date for rework
Planned End Date | Planned End date for rework
Actual Start Date | Actual start date for rework
Actual End date | Actual End date for rework
Actual Effort Spent | Actual time taken to close the defect (in hrs.)
Status | Mention status as follows: Open Closed Accepted Fixed Work In Progress Postponed Reassigned Rejected
Remarks | Remarks, if any.