## Issues_Tracking_Register
ISSUE MANAGEMENT LOG
ID | Issue Description | Date/Time of reporting | Current Status | Priority | Assigned To | Expected Resolution Date | Escalation Required (Y/N)? | Action Steps | Entered By | Actual Resolution Date | Final Resolution & Rationale
| EXAMPLE: The project is short on a specific skill set. | 2014-07-23 11:00 | Open | Critical |  |  | Yes | EXAMPLE: Meet with board members to clarify the project finances | John Doe |  | EXAMPLE: The project team met with board members to clarify the project finances, allowing the project to move forward as planned.
| EXAMPLE: Negotiations with functional managers in an organization competing for scarce human resources are forecasted to delay project completion. |  | Work In Progress | High |  |  | No | EXAMPLE: Add staff to fill the skills gap. | Jane Doe |  | EXAMPLE: Staff was added to the project to fill the skills gap.
Note on A2: • ID: A unique ID number used to identify the issue in the issue tracking log.
Note on B2: • Issue Description: This column should be populated with a description of the issue.
Note on D2: • Current Status: This column should be populated with the issue's current status. o Open: The issue is currently open but has not yet been addressed. o Work In Progress: The issue is being actively worked to develop a resolution. o Closed: The issue is no longer considered an active project threat and can be closed with or without resolution. Some other potential options include: o Late: The issue resolution is not yet resolved and it is past the expected resolution date. o On Hold: The issue has been put on hold. o Combined: Two issues found to be similar have been combined.
Note on E2: • Priority: This column should be populated with the priority of the issue. Valid options include the following: High, Medium, Low. These are defined as follows: o Critical: Issue will stop project progress if not resolved. o High: Issue will likely move the project back in terms of budget or timeline, or will materially affect quality or scope. o Medium: Issue will have material effect on project, has potential to be moved to high category and/or requires significant resources to manage. o Low: Issue is expected to have a moderate effect on the project, but will require resources to address.
Note on F2: • Assigned To Owner: This column should be populated by the name of the issues owner. The individual most responsible for working towards resolving the issue.
Note on G2: • Expected Resolution Date: This column should be populated with the date that the issue is expected to be resolved.
Note on H2: • Escalation Required (Y/N): This column should be populated with “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
Note on I2: • Action Steps: This column should be populated with the proposed steps to address the issue. Examples include, but are not limited to, developing alternatives analysis or submitting a change request.
Note on J2: • Entered By: This column should be populated by the name of the individual who first identified the issue.
Note on K2: • Actual Resolution Date: This column should be populated with the date that the issue was actually resolved.
Note on L2: • Final Resolution & Rationale: This column should be populated with a description of the final resolution & rationale of the issue. The resolution may be expressed in terms of one or more of the following: schedule, scope, resources, and space. The resolution description should also include a reference to the milestones impacted.